## Sheet1
Task Name | Late Start | Late Finish | Free Slack | Total Slack
Government Permits | Tue 12/04/22 | Tue 19/04/22 | 0 days | 117 days
Bedrock Survey | Wed 09/03/22 | Tue 19/04/22 | 0 days | 92 days
Estimation and Budgeting | Tue 12/04/22 | Tue 19/04/22 | 0 days | 116 days
Project Scheduling | Wed 03/11/21 | Fri 05/11/21 | 0 days | 3 days
Paperworks completion | Tue 19/04/22 | Tue 19/04/22 | 0 days | 92 days
Technical Drawings | Tue 29/03/22 | Tue 19/04/22 | 0 days | 92 days
Architectural Renderings | Thu 07/04/22 | Tue 19/04/22 | 0 days | 92 days
Site Plan Design | Tue 19/04/22 | Tue 19/04/22 | 92 days | 92 days
Job Notification | Mon 28/02/22 | Fri 18/03/22 | 0 days | 86 days
Screening | Fri 11/03/22 | Fri 18/03/22 | 0 days | 86 days
Assessment | Mon 14/03/22 | Fri 18/03/22 | 0 days | 86 days
Contract | Wed 16/03/22 | Fri 18/03/22 | 0 days | 86 days
Recruitment | Tue 19/04/22 | Tue 19/04/22 | 107 days | 107 days
Overseas Transportation | Thu 14/04/22 | Tue 19/04/22 | 108 days | 108 days
International Training | Fri 18/03/22 | Tue 19/04/22 | 0 days | 86 days
Local workforce Training | Thu 07/04/22 | Tue 19/04/22 | 0 days | 86 days
Safety Training | Thu 07/04/22 | Tue 19/04/22 | 0 days | 86 days
Training completion | Tue 19/04/22 | Tue 19/04/22 | 86 days | 86 days
Specification | Tue 29/03/22 | Mon 04/04/22 | 0 days | 105 days
Quotation & Tender Approval | Mon 04/04/22 | Wed 13/04/22 | 0 days | 105 days
Issuing PO | Thu 14/04/22 | Tue 19/04/22 | 0 days | 105 days
Procurement | Tue 19/04/22 | Tue 19/04/22 | 105 days | 105 days
Warehouse | Tue 23/11/21 | Tue 19/04/22 | 0 days | 5 days
Inventory Monitoring | Thu 18/11/21 | Tue 19/04/22 | 0 days | 2 days
Storage Management | Tue 19/04/22 | Tue 19/04/22 | 2 days | 2 days
logistics management | Tue 19/04/22 | Tue 19/04/22 | 81 days | 81 days
Awareness Campaign | Fri 05/11/21 | Wed 10/11/21 | 0 days | 3 days
Handling Protest Groups | Wed 10/11/21 | Mon 15/11/21 | 0 days | 3 days
Social Awarenss | Mon 15/11/21 | Mon 15/11/21 | 0 days | 3 days
Debris Removal | Mon 15/11/21 | Fri 03/12/21 | 0 days | 3 days
Pathways Clearing | Thu 07/04/22 | Tue 19/04/22 | 0 days | 97 days
Removal of Prince Stage | Wed 23/03/22 | Tue 12/04/22 | 0 days | 86 days
Pollution Monitoring | Fri 10/12/21 | Tue 19/04/22 | 22 days | 22 days
Utlities Connection | Wed 13/04/22 | Tue 19/04/22 | 94 days | 94 days
Site Preparation | Tue 12/04/22 | Tue 12/04/22 | 0 days | 86 days
Isolating worksite | Tue 12/04/22 | Tue 19/04/22 | 0 days | 86 days
Installing survaillance cameras | Wed 13/04/22 | Tue 19/04/22 | 0 days | 86 days
Security Measures | Tue 19/04/22 | Tue 19/04/22 | 86 days | 86 days
Setout | Fri 03/12/21 | Wed 08/12/21 | 0 days | 3 days
Excavation | Wed 08/12/21 | Mon 10/01/22 | 0 days | 3 days
Concrete | Mon 10/01/22 | Mon 28/02/22 | 0 days | 3 days
Foundation | Mon 28/02/22 | Mon 28/02/22 | 0 days | 3 days
Walls & Separations | Mon 28/02/22 | Tue 19/04/22 | 0 days | 3 days
Doors | Thu 07/04/22 | Tue 19/04/22 | 3 days | 3 days
Electrical | Mon 07/03/22 | Thu 14/04/22 | 0 days | 1 day
Plumbing | Tue 29/03/22 | Tue 19/04/22 | 14 days | 14 days
HVAC & Insulation | Thu 07/04/22 | Tue 19/04/22 | 17 days | 17 days
Flooring | Fri 25/03/22 | Thu 14/04/22 | 0 days | 1 day
Internal Painting | Tue 05/04/22 | Thu 14/04/22 | 0 days | 1 day
Furnishing | Tue 05/04/22 | Thu 14/04/22 | 0 days | 1 day
Internal | Thu 14/04/22 | Thu 14/04/22 | 0 days | 1 day
Roof | Fri 18/03/22 | Tue 19/04/22 | 0 days | 1 day
Windows & Panelling | Tue 29/03/22 | Tue 19/04/22 | 0 days | 1 day
External | Tue 19/04/22 | Tue 19/04/22 | 1 day | 1 day
Taxi Rank & Car parking | Wed 09/03/22 | Tue 19/04/22 | 3 days | 3 days
Link Bridge | Wed 23/02/22 | Wed 13/04/22 | 0 days | 21 days
Debris Removal | Thu 07/04/22 | Wed 13/04/22 | 0 days | 21 days
Demobilization | Wed 13/04/22 | Tue 19/04/22 | 2 days | 21 days